## Business summary
Call Analysis - what the business gets from each release
Release | Business outcome | What business users receive | Completion signal
R0 - Groundwork (Internal) | Nothing visible to the business yet. The data structures are built and the first list of call categories and subcategories is agreed with the call center leads. Everything built afterwards adds to this base rather than reworking it. | • A category and subcategory list to review and sign off. | The call center has signed off the first category list and the tables are in place.
R1 - Every call categorized (First value) | Every call is broken into the topics discussed (for example crown coverage, then finding a dentist) and each topic is given a category and subcategory. Results are stored with our own data, not locked in Genesys, and reports come out of the system instead of being compiled by hand. No detail below subcategory yet. | • A report for any group, payer or caller type: number and share of calls by category and subcategory, for any period. • The CareSource Ohio PCIR and PCDR reports produced by the system each month. • A record of which category version was used for any call. | Every incoming call is categorized automatically and the manual CareSource reporting stops.
R2 - Actionable detail and a dashboard (Main payoff) | Knowing that half of calls are about benefits is not enough to act on. This release captures the specifics behind each subcategory: which procedure code; whether the caller asked about coverage, the maximum or the deductible; whether the dentist list was emailed or read over the phone; whether the toolkit problem was a password or an MFA code. The data opens up in an interactive dashboard. | • An interactive dashboard: last 30, 60 or 90 days, filtered by caller type, group or program, top categories by volume, drill-down into the specifics of a subcategory. • The same data available to Power BI or Tableau for building your own views. | The call center confirms the detail is specific enough to act on for benefits and eligibility, provider search and toolkit.
R3 - The system learns, the business decides (Growth) | The system reviews what members and providers have been asking and proposes categories and subcategories that are not yet in the list. The business approves or rejects each proposal; approved changes apply to new calls from that point without a feature-team request. Trends over time appear on the dashboard, and chatbot conversations join the analysis. | • Proposed category updates to approve or reject. • Period-over-period comparison on the dashboard, overall or for one group. • Chatbot sessions categorized, with whether the bot fulfilled the request. | A category proposed by the system has been approved by the business and is in use for new calls.
R4 - Ask anything (Exploration) | Instead of waiting for a report, ask the question directly, and surface questions nobody thought to ask. | • A plain-language question interface over the data ("what were GM members calling about last month?"). • Keyword search over a time window (mentions of a mailer since it went out). • Wrong-queue and other-plan call counts. | A call center manager answers a question nobody planned for, without asking IT.

## Side by side
Releases and features side by side
Release: | R1
Releases |  |  | Features
Release | Name | Goal | Release | ID | Feature | Description
R0 | Foundation (internal) | Put the data structures and the agreed taxonomy in place so that everything after it is additive. No user-facing deliverable. | R0 | F1 | Analytics data model | One interaction-analysis record per call; one topic record per distinct subject discussed on the call (one-to-many). Each topic carries its category, subcategory and a short description of what was discussed, used later for category discovery. The structure allows drill-down attributes to be added per topic without breaking changes. Findings attach to the interaction; group, caller type and channel are resolved through the interaction tables, not copied.
R1 | Categorize and report | Every call is broken into the topics discussed and each topic is categorized (category and subcategory only). Canned reports come out of the system. | R0 | F2 | Taxonomy storage with versions and audit trail | Tables for the category / subcategory tree, client-specific sets, set versions and applicability (payer, plan, group, subgroup). Categories are immutable; a change creates a new row and a new version. Every change records who made it and when.
R2 | Drill down | Beyond category and subcategory, capture the specifics of each topic (which procedure, which benefit, which provider) and make the data explorable. | R0 | F3 | Taxonomy v1 agreed with the call center | First member and provider category / subcategory trees, drafted by the team and reviewed with the call center leads. Loaded as version 1 (scripted).
R3 | Discover and curate | The system proposes new categories from what it sees in the calls; the business approves them. Trends over time become visible. | R0 | F4 | Client-specific sets and opt-out | CareSource Ohio PCIR and PCDR sets loaded and bound to the payer; plans that do not approve AI processing are listed for exclusion.
R4 | Explore | Ask any question of the data. | R1 | F5 | Topic decomposition and categorization of every call | After summarization, each transcript is split into the distinct topics discussed (e.g. crown coverage, then find a dentist; or the same question about three different patients). Each topic is assigned a category and subcategory from the active taxonomy, plus any client-specific set that applies, and stored with the set version and a short description. Caller type comes from the interaction, not the model. Category and subcategory only; no deeper extraction yet.
|  |  | R1 | F6 | Primary category per call | Each call also records the primary category, so headline reports can count calls as well as topics.
|  |  | R1 | F7 | Taxonomy maintenance | A basic internal screen to view versions, add or retire categories and publish a new version. If not built in R1, taxonomy changes are scripted until it exists.
|  |  | R1 | F8 | Data available in Snowflake | The new tables flow to Snowflake through the existing RCST stream.
|  |  | R1 | F9 | Canned reports | Call volume and percentage by category and subcategory, selectable by group, payer or caller type. Includes CareSource Ohio PCIR and PCDR, replacing the manual monthly process.
|  |  | R2 | F10 | Drill-down extraction per subcategory | For each subcategory, extract the specifics that make it actionable: e.g. covered procedure - which procedure code; find a dentist - zip code search, list emailed vs read by phone; toolkit - password vs MFA. The attribute list is configured per subcategory, reviewed with the business on sample output, and stored without schema changes.
|  |  | R2 | F11 | Targeted reprocessing | When an extraction definition or a taxonomy branch changes, re-run only the topics under that node or within a date range.
|  |  | R2 | F12 | Snowflake tables for reporting | Denormalized tables joining topics to caller type, channel, group, subgroup and program, plus the aggregates the dashboard needs.
|  |  | R2 | F13 | Interactive dashboard (pre-built) | Top categories and subcategories by volume for the last 30, 60 or 90 days; filter by caller type, group, subgroup and program (commercial vs government); drill into the extracted specifics of a subcategory. No period-over-period comparison yet.
|  |  | R2 | F14 | Self-service BI | The same Snowflake tables are available to Power BI / Tableau users to build their own views.
|  |  | R3 | F15 | Category discovery | Periodic clustering over the stored topic descriptions surfaces categories and subcategories not in the tree (including what currently lands in 'other').
|  |  | R3 | F16 | Proposed version and approval | A discovery run produces a proposed new taxonomy version. The business reviews, approves or rejects it; an approved version becomes the active set for new calls. Business users can also manage sets, versions and applicability directly, without a feature-team change.
|  |  | R3 | F17 | Trend analysis | Month-over-month and period comparison on the dashboard, including within a single group.
|  |  | R3 | F18 | Chatbot sessions | Chatbot transcripts run through the same pipeline, with a record of whether the bot fulfilled the request.
|  |  | R4 | F19 | Chat with the data | Conversational questions over the Snowflake data via its semantic layer.
|  |  | R4 | F20 | Ad-hoc mining and keyword search | User-defined filters, time windows and keyword search across topics and transcripts.
|  |  | R4 | F21 | AI-suggested patterns | AI reviews a set of topics (e.g. all denture questions for a group) and suggests patterns or attributes worth capturing and reporting.
|  |  | R4 | F22 | Routing and misroute analysis | Original queue vs actual group; cross-plan transfers; effect of IVR changes. Needs Genesys queue data.
|  |  | R4 | F23 | Predictive use and e-mail channel | Forecast volume for large-group conversions; categorize e-mail inquiries.

## All features
All features by release (filterable)
Release | ID | Feature | Description | Status
R0 | F1 | Analytics data model | One interaction-analysis record per call; one topic record per distinct subject discussed on the call (one-to-many). Each topic carries its category, subcategory and a short description of what was discussed, used later for category discovery. The structure allows drill-down attributes to be added per topic without breaking changes. Findings attach to the interaction; group, caller type and channel are resolved through the interaction tables, not copied.
R0 | F2 | Taxonomy storage with versions and audit trail | Tables for the category / subcategory tree, client-specific sets, set versions and applicability (payer, plan, group, subgroup). Categories are immutable; a change creates a new row and a new version. Every change records who made it and when.
R0 | F3 | Taxonomy v1 agreed with the call center | First member and provider category / subcategory trees, drafted by the team and reviewed with the call center leads. Loaded as version 1 (scripted).
R0 | F4 | Client-specific sets and opt-out | CareSource Ohio PCIR and PCDR sets loaded and bound to the payer; plans that do not approve AI processing are listed for exclusion.
R1 | F5 | Topic decomposition and categorization of every call | After summarization, each transcript is split into the distinct topics discussed (e.g. crown coverage, then find a dentist; or the same question about three different patients). Each topic is assigned a category and subcategory from the active taxonomy, plus any client-specific set that applies, and stored with the set version and a short description. Caller type comes from the interaction, not the model. Category and subcategory only; no deeper extraction yet.
R1 | F6 | Primary category per call | Each call also records the primary category, so headline reports can count calls as well as topics.
R1 | F7 | Taxonomy maintenance | A basic internal screen to view versions, add or retire categories and publish a new version. If not built in R1, taxonomy changes are scripted until it exists.
R1 | F8 | Data available in Snowflake | The new tables flow to Snowflake through the existing RCST stream.
R1 | F9 | Canned reports | Call volume and percentage by category and subcategory, selectable by group, payer or caller type. Includes CareSource Ohio PCIR and PCDR, replacing the manual monthly process.
R2 | F10 | Drill-down extraction per subcategory | For each subcategory, extract the specifics that make it actionable: e.g. covered procedure - which procedure code; find a dentist - zip code search, list emailed vs read by phone; toolkit - password vs MFA. The attribute list is configured per subcategory, reviewed with the business on sample output, and stored without schema changes.
R2 | F11 | Targeted reprocessing | When an extraction definition or a taxonomy branch changes, re-run only the topics under that node or within a date range.
R2 | F12 | Snowflake tables for reporting | Denormalized tables joining topics to caller type, channel, group, subgroup and program, plus the aggregates the dashboard needs.
R2 | F13 | Interactive dashboard (pre-built) | Top categories and subcategories by volume for the last 30, 60 or 90 days; filter by caller type, group, subgroup and program (commercial vs government); drill into the extracted specifics of a subcategory. No period-over-period comparison yet.
R2 | F14 | Self-service BI | The same Snowflake tables are available to Power BI / Tableau users to build their own views.
R3 | F15 | Category discovery | Periodic clustering over the stored topic descriptions surfaces categories and subcategories not in the tree (including what currently lands in 'other').
R3 | F16 | Proposed version and approval | A discovery run produces a proposed new taxonomy version. The business reviews, approves or rejects it; an approved version becomes the active set for new calls. Business users can also manage sets, versions and applicability directly, without a feature-team change.
R3 | F17 | Trend analysis | Month-over-month and period comparison on the dashboard, including within a single group.
R3 | F18 | Chatbot sessions | Chatbot transcripts run through the same pipeline, with a record of whether the bot fulfilled the request.
R4 | F19 | Chat with the data | Conversational questions over the Snowflake data via its semantic layer.
R4 | F20 | Ad-hoc mining and keyword search | User-defined filters, time windows and keyword search across topics and transcripts.
R4 | F21 | AI-suggested patterns | AI reviews a set of topics (e.g. all denture questions for a group) and suggests patterns or attributes worth capturing and reporting.
R4 | F22 | Routing and misroute analysis | Original queue vs actual group; cross-plan transfers; effect of IVR changes. Needs Genesys queue data.
R4 | F23 | Predictive use and e-mail channel | Forecast volume for large-group conversions; categorize e-mail inquiries.

## R0 Foundation
R0 - Foundation (internal)
Goal: Put the data structures and the agreed taxonomy in place so that everything after it is additive. No user-facing deliverable.
What you get: Nothing yet - this is groundwork. The tables and the first taxonomy exist and have been agreed with the call center.
Features
ID | Feature | Description | Status
F1 | Analytics data model | One interaction-analysis record per call; one topic record per distinct subject discussed on the call (one-to-many). Each topic carries its category, subcategory and a short description of what was discussed, used later for category discovery. The structure allows drill-down attributes to be added per topic without breaking changes. Findings attach to the interaction; group, caller type and channel are resolved through the interaction tables, not copied.
F2 | Taxonomy storage with versions and audit trail | Tables for the category / subcategory tree, client-specific sets, set versions and applicability (payer, plan, group, subgroup). Categories are immutable; a change creates a new row and a new version. Every change records who made it and when.
F3 | Taxonomy v1 agreed with the call center | First member and provider category / subcategory trees, drafted by the team and reviewed with the call center leads. Loaded as version 1 (scripted).
F4 | Client-specific sets and opt-out | CareSource Ohio PCIR and PCDR sets loaded and bound to the payer; plans that do not approve AI processing are listed for exclusion.

## R1 Categorize and report
R1 - Categorize and report
Goal: Every call is broken into the topics discussed and each topic is categorized (category and subcategory only). Canned reports come out of the system.
What you get: Reports by group, payer or caller type showing call volume and percentage by category and subcategory. CareSource PCIR and PCDR produced by the system instead of by hand.
Features
ID | Feature | Description | Status
F5 | Topic decomposition and categorization of every call | After summarization, each transcript is split into the distinct topics discussed (e.g. crown coverage, then find a dentist; or the same question about three different patients). Each topic is assigned a category and subcategory from the active taxonomy, plus any client-specific set that applies, and stored with the set version and a short description. Caller type comes from the interaction, not the model. Category and subcategory only; no deeper extraction yet.
F6 | Primary category per call | Each call also records the primary category, so headline reports can count calls as well as topics.
F7 | Taxonomy maintenance | A basic internal screen to view versions, add or retire categories and publish a new version. If not built in R1, taxonomy changes are scripted until it exists.
F8 | Data available in Snowflake | The new tables flow to Snowflake through the existing RCST stream.
F9 | Canned reports | Call volume and percentage by category and subcategory, selectable by group, payer or caller type. Includes CareSource Ohio PCIR and PCDR, replacing the manual monthly process.
User stories (draft, for business sign-off)
# | Story
1 | As a call center manager, I can get a report for any group, payer or caller type showing the number and percentage of calls and topics by category and subcategory for a chosen period.
2 | As the CareSource reporting owner, I can produce the monthly PCIR and PCDR reports from the system without manual categorization.
3 | As a call center lead, I can see which taxonomy version was used to categorize any given call.

## R2 Drill down
R2 - Drill down
Goal: Beyond category and subcategory, capture the specifics of each topic (which procedure, which benefit, which provider) and make the data explorable.
What you get: An interactive dashboard: top categories by volume for the last 30, 60 or 90 days, filterable by caller type, group and program, with drill-down into the specifics of each subcategory. The same data is available for self-service in Power BI or Tableau.
Features
ID | Feature | Description | Status
F10 | Drill-down extraction per subcategory | For each subcategory, extract the specifics that make it actionable: e.g. covered procedure - which procedure code; find a dentist - zip code search, list emailed vs read by phone; toolkit - password vs MFA. The attribute list is configured per subcategory, reviewed with the business on sample output, and stored without schema changes.
F11 | Targeted reprocessing | When an extraction definition or a taxonomy branch changes, re-run only the topics under that node or within a date range.
F12 | Snowflake tables for reporting | Denormalized tables joining topics to caller type, channel, group, subgroup and program, plus the aggregates the dashboard needs.
F13 | Interactive dashboard (pre-built) | Top categories and subcategories by volume for the last 30, 60 or 90 days; filter by caller type, group, subgroup and program (commercial vs government); drill into the extracted specifics of a subcategory. No period-over-period comparison yet.
F14 | Self-service BI | The same Snowflake tables are available to Power BI / Tableau users to build their own views.
User stories (draft, for business sign-off)
# | Story
1 | As a call center manager, I can open a dashboard, choose the last 30, 60 or 90 days, filter by caller type, group and program, and see the top categories and subcategories by volume.
2 | As a call center manager, I can drill from a subcategory (e.g. covered procedure) into the specifics captured for it (e.g. which procedure codes were asked about most).
3 | As an analyst, I can connect Power BI or Tableau to the Snowflake tables and build my own view.

## R3 Discover and curate
R3 - Discover and curate
Goal: The system proposes new categories from what it sees in the calls; the business approves them. Trends over time become visible.
What you get: A proposed taxonomy update that the business can approve or reject, period-over-period comparison on the dashboard, and chatbot sessions included in the analysis.
Features
ID | Feature | Description | Status
F15 | Category discovery | Periodic clustering over the stored topic descriptions surfaces categories and subcategories not in the tree (including what currently lands in 'other').
F16 | Proposed version and approval | A discovery run produces a proposed new taxonomy version. The business reviews, approves or rejects it; an approved version becomes the active set for new calls. Business users can also manage sets, versions and applicability directly, without a feature-team change.
F17 | Trend analysis | Month-over-month and period comparison on the dashboard, including within a single group.
F18 | Chatbot sessions | Chatbot transcripts run through the same pipeline, with a record of whether the bot fulfilled the request.
User stories (draft, for business sign-off)
# | Story
1 | As a call center lead, I receive a proposed taxonomy update generated from the calls and can approve or reject it; an approved version is used for new calls from that point.
2 | As a call center manager, I can compare category volumes between two periods, overall or for one group.
3 | As a digital channel owner, I can see what members asked the chatbot and whether the bot fulfilled the request.

## R4 Explore
R4 - Explore
Goal: Ask any question of the data.
What you get: A conversational interface over the data, keyword and ad-hoc search, routing and misroute analysis, and AI-suggested patterns worth reporting on.
Features
ID | Feature | Description | Status
F19 | Chat with the data | Conversational questions over the Snowflake data via its semantic layer.
F20 | Ad-hoc mining and keyword search | User-defined filters, time windows and keyword search across topics and transcripts.
F21 | AI-suggested patterns | AI reviews a set of topics (e.g. all denture questions for a group) and suggests patterns or attributes worth capturing and reporting.
F22 | Routing and misroute analysis | Original queue vs actual group; cross-plan transfers; effect of IVR changes. Needs Genesys queue data.
F23 | Predictive use and e-mail channel | Forecast volume for large-group conversions; categorize e-mail inquiries.
User stories (draft, for business sign-off)
# | Story
1 | As a call center manager, I can ask a question in plain language (e.g. 'what were GM members calling about last month?') and get an answer from the data.
2 | As an analyst, I can search calls by keyword over a time window (e.g. mentions of a mailer since it was sent).
3 | As a call center manager, I can see how many calls arrived on the wrong queue or were for another Delta Dental plan.